## Example
Project Name | Main Street Bicycle Improvements
Date Created | 2021-07-30
|  | Grant Funds |  |  |  | Cash Match |  |  |  | In-Kind Match |  |  |  | Item Total
Ref. # | Short Description | Qty. | Units | Cost | Subtotal | Qty. | Units | Cost | Subtotal | Qty. | Units | Cost | Subtotal |  | Justification | Implementation Timeframe
1 | Shared Lane Pavement Markings | 10 | Stencils | 250 | 2500 | 10 | Stencils | 250 | 2500 |  |  |  | 0 | 5000 | Assumes cost per bicycle lane marking of $250.00 based on three vendor quotes. | April of 2022
2 | Installation of Pavement Markings |  |  |  | 0 |  |  |  | 0 | 20 | Stencils | 125 | 2500 | 2500 | The installation of the shared lane pavement markings will be accomplished by paid staff an an in-kind match. | August of 2022
3 | Website Development |  |  |  | 0 |  |  |  | 0 | 20 | Hours | 24.9 | 498 | 498 | A town resident who works with websites professionally will create a website to promote the improvements as in-kind match. | Project website will be completed no later than March 2022
4 | Project Engineering | 5 | Hours | 100 | 500 |  |  |  | 0 |  |  |  | 0 | 500 | The services of a licensed engineer will be utilized to review the final design and proposed placement of the pavement markings. | April of 2022
5 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
6 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
7 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
8 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
9 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
10 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
11 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
12 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
13 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
14 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
15 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
16 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
17 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
18 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
19 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
20 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Grant Total: |  |  | 3000 | Cash Match Total: |  |  | 2500 | In-Kind Match Total: |  |  | 2998 | 8498
Note on C3: Henry Underwood: Grant funds requested by the project
Note on G3: Henry Underwood: Monetary contributions to the project
Note on K3: Henry Underwood: Non-cash contributions to the project (such as labor, volunteer time, supplies, equipment, and services)
Note on B4: Henry Underwood: Describe the service, material, or resource
Note on P4: Henry Underwood: Please justify the total estimated cost for each budget item along with any assumptions that went into the estimate.
Note on Q4: Henry Underwood: Approximate implementation date
Note on M8: Henry Underwood: Cost is based on 2016 value of volunteer time for New Hampshire published by Independent Sector (http://independentsector.org).

## Blank Template
Project Name
Date Created
|  | Grant Funds |  |  |  | Cash Match |  |  |  | In-Kind Match |  |  |  | Item Total
Ref. # | Short Description | Qty. | Units | Cost | Subtotal | Qty. | Units | Cost | Subtotal | Qty. | Units | Cost | Subtotal |  | Justification | Implementation Timeframe
1 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
2 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
3 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
4 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
5 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
6 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
7 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
8 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
9 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
10 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
11 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
12 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
13 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
14 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
15 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
16 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
17 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
18 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
19 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
20 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Grant Total: |  |  | 0 | Cash Match Total: |  |  | 0 | In-Kind Match Total: |  |  | 0 | 0

## ESRI_MAPINFO_SHEET (hidden)
DO NOT EDIT
For Esri use only